## Cover Page
Medicus Clinical Safety Hazard Log
Clinical Safety Officer | Dr Imran Khan | Status | Approved
Version | 1 | Date of Export | 9 December 2022
Clinical Safety Hazard Log
Document Purpose
This document is intended to help organisations using Medicus comply with clinical safety obligations. Our Hazard Log and Clinical Safety Management System is operated in Jira and Confluence and then exported for use by our customers.
Copyright © 2022 Medicus Health Ltd

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## Authentication & Access Control
| Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk
ID | Hazard Description |  | Causes |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Hazard | Potential Clinical Impact | Possible Cause | Cause ID | Date Added | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
HAZ-239 | User is unable to interact with NHS Spine services | Delay to care. | Incorrect RBAC activity codes on the user’s Smartcard (CIS2) | HAZ-253 | 5 December 2022 |  |  |  |  | The local registration authority has their own processes for issuing Smartcards to NHS staff. |  | Considerable | Low | 2 | There is a likelihood that there could be significant clinical risk. | Where a specific CIS2 Activity Code is required to perform an action on the NHS Spine, Medicus checks whether the user has the correct activity code to perform the action at that organisation. | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. |  |  |  | Individual healthcare organisations must register staff members for the correct Smartcard roles. | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Unavailability of NHS CIS2 service for login | HAZ-254 | 13 October 2022 | NHS Digital have graded CIS2 a “platinum service” which means that it has the highest availability and Service Level Agreement guarantees - [https://digital.nhs.uk/services/identity-and-access-management/nhs-care-identity-service-2/care-identity-authentication/integration-toolkit/client-service-management¦https://digital.nhs.uk/services/identity-and-access-management/nhs-care-identity-service-2/care-identity-authentication/integration-toolkit/client-service-management] |  |  |  | Healthcare professionals should already be able to operate without NHS Spine services. |  | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. | [6 empty] | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User Smartcard forgotten, lost or Smartcard not working | HAZ-255 | 13 October 2022 |  |  |  |  | Healthcare professionals should already be able to operate without NHS Spine services. |  | Considerable | Low | 2 | There is a likelihood that there could be significant clinical risk. | [6 empty] | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User has not configured their Smartcard with Medicus correctly | HAZ-256 | 13 October 2022 | [6 empty] | Considerable | Low | 2 | There is a likelihood that there could be significant clinical risk. | On initial login, the user accesses Medicus with their local authentication credentials and then navigates to the “My Account” area of Medicus to pair their CIS2 account. When the user clicks “Pair”, a request is made to the CIS2 service and the user is prompted to login with CIS2 (e.g. enter their Smartcard PIN). Once the user has successfully authenticated with CIS2, the accounts are paired and the user can use CIS2 as a Single Sign On (SSO) and interact with NHS Spine services such as PDS. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/managing-your-user-account¦https://medicus.scrollhelp.site/support/managing-your-user-account] |  |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-275 | User has access to Medicus but cannot access the areas they need | Delay to care or clinician is unable to complete an assessment. | Medicus has been incorrectly configured | HAZ-278 | 5 December 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Medicus implements a local authentication and access control model for regular interactions with the Medicus application. Each user is assigned “User Roles” which grant access to “Permissions” that control what users ca do and see within the Medicus app. Additionally, Medicus integrates with the NHS CIS2 service (Smartcards) for features that require NHS Spine services such as Personal Demographic Service, e-Referral Service, Electronic Prescription Service, Summary Care Record. Users can “pair” their CIS2 user account with their Medicus account. | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/authentication-access-control¦https://medicus.scrollhelp.site/support/authentication-access-control] | Each healthcare organisation requires their own local processes to manage user access to Medicus. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-276 | User can access restricted areas for their role | Inappropriate care being given by unauthorised users. | Medicus has been incorrectly configured | HAZ-279 | 5 December 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Medicus implements a local authentication and access control model for regular interactions with the Medicus application. Each user is assigned “User Roles” which grant access to “Permissions” that control what users ca do and see within the Medicus app Additionally, Medicus integrates with the NHS CIS2 service (Smartcards) for features that require NHS Spine services such as Personal Demographic Service, e-Referral Service, Electronic Prescription Service, Summary Care Record. Users can “pair” their CIS2 user account with their Medicus account. | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/authentication-access-control¦https://medicus.scrollhelp.site/support/authentication-access-control] | Each healthcare organisation requires their own local processes to manage user access to Medicus. |  | Minor | Medium | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-280 | User can incorrectly interact with NHS Spine services | Delay to care or inappropriate patient care. | Incorrect RBAC activity codes on the user’s Smartcard (CIS2) | HAZ-281 | 5 December 2022 |  |  |  |  | The local registration authority has their own processes for issuing Smartcards to NHS staff. |  | Considerable | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Where a specific CIS2 Activity Code is required to perform an action on the NHS Spine, Medicus checks whether the user has the correct activity code to perform the action at that organisation. | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. |  |  | Individual healthcare organisations must register staff members for the correct Smartcard roles. |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-65 | User is incorrectly given access to Medicus | Patient could receive care that isn’t authorised by the appropriate clinician. | Incorrect user access controls | HAZ-277 | 5 December 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Medicus implements a local authentication and access control model for regular interactions with the Medicus application. Each user is assigned “User Roles” which grant access to “Permissions” that control what users ca do and see within the Medicus app. Additionally, Medicus integrates with the NHS CIS2 service (Smartcards) for features that require NHS Spine services such as Personal Demographic Service, e-Referral Service, Electronic Prescription Service, Summary Care Record. Users can “pair” their CIS2 user account with their Medicus account. | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/authentication-access-control¦https://medicus.scrollhelp.site/support/authentication-access-control] | Each healthcare organisation requires their own local processes to manage user access to Medicus. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.

## Interoperability
| Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk
ID | Hazard Description |  | Causes |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Hazard | Potential Clinical Impact | Possible Cause | Cause ID | Date Added | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
HAZ-221 | User unable to view the Intersystems Shared Care Record | Possible inappropriate care, delay to care. | Intersystems Shared Care Record unavailable | HAZ-229 | 12 October 2022 | [6 empty] | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. | To enable the Intersystems Shared Care Record for a tenant, there is a “tenant setting” called “Intersystems Settings” with the properties “enabled” and “environment” (UAT or Live). When an organisation uses Intersystems as their Shared Care Record, Medicus enables the tenant setting. Medicus has a certificate which makes us a trusted supplier and request the URL for a patient to load the Shared Care Record in an iFrame. |  |  |  | Individual healthcare organisations need to be able to operate without the shared care record for business continuity purposes in scenarios which require this. |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User is not connected to the HSCN network | HAZ-271 | 11 November 2022 | [6 empty] | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. |  |  |  |  | Individual healthcare organisations need to be able to operate without the shared care record for business continuity purposes in scenarios which require this. |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-286 | User views out of date information on Intersystems Shared Care Record |  | Information out of date compared to source system | HAZ-287 | 5 December 2022 | [6 empty] | Considerable | Low | 2 | There is a likelihood that there could be significant clinical risk. | Each time the Shared Care Record is rendered in Medicus, we obtain a new URL from Intersystems to ensure that the latest data is retrieved (e.g. we do not cache the URL). When the Shared Care Record is retrieved, Intersystems clearly displays when the data was last updated. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. |  |  |  |  | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk.

## Patient Information Maintenance
| Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk
ID | Hazard Description |  | Causes |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Hazard | Potential Clinical Impact | Possible Cause | Cause ID | Date Added | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
HAZ-195 | Patient misidentification or incorrect patient identification when using PDS | Possible inappropriate care, delay to care, lack of care. | Incorrect data entered by the user for the search | HAZ-199 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | Once the results of a PDS search have been returned, Medicus displays the name of the patient and additional demographic details to help initially identify the patient. After a patient has been chosen from the search results, Medicus then presents a confirmation step with additional PDS information to help the user be confident that they have chosen the right PDS record. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Multiple PDS search results returned, user selects wrong one | HAZ-202 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | Once the results of a PDS search have been returned, Medicus displays the name of the patient and additional demographic details to help initially identify the patient. After a patient has been chosen from the search results, Medicus then presents a confirmation step with additional PDS information to help the user be confident that they have chosen the right PDS record. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Complex search factors | HAZ-205 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. |  |  | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Unavailability of NHS PDS service | HAZ-206 | 11 October 2022 | NHS Digital provide high availability SLAs for the PDS. |  |  |  | Healthcare professionals should already be able to operate without NHS Spine services and may need to revert to other business continuity procedures without the use of Medicus. |  | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. | [6 empty] | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Inability to differentiate between patients with similar information | HAZ-207 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | Multiple points of information are displayed on screen to the user when returning search results to enable them to correctly identify the patient. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User selects a deceased patient | HAZ-208 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | When the PDS indicates that a patient is deceased, Medicus displays a deceased badge on the result. Where appropriate (based on the workflow), the result is disabled and the user is unable to select that patient. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] |  |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Data quality issues in PDS | HAZ-209 | 11 October 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. |  |  |  |  | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User selects a patient flagged as sensitive on the PDS | HAZ-213 | 11 October 2022 | [6 empty] | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. | The PDS does not return address or contact information for patients who are flagged as sensitive (restricted or very restricted) on the PDS. When a sensitive record is returned, a badge showing “Sensitive Record” is displayed on the result card for that patient. Once a sensitive record has been persisted into Medicus, the patient banner / information panel shows the sensitive record badge. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds¦https://medicus.scrollhelp.site/support/searching-for-a-patient-on-the-pds] | Healthcare organisation should have a local policy for handling sensitive patient registrations. |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-237 | Local Medicus record not updated correctly from PDS | Possible inappropriate care, delay to care, lack of care. | Duplicate and superseded patient records | HAZ-234 | 13 October 2022 | [6 empty] | Considerable | Very Low | 2 | There is a likelihood that there could be significant clinical risk. | If Medicus retrieves a superseded PDS record, it checks whether there is another local patient record with the same NHS number. If there is no local patient record with that NHS number, it updates the NHS number on the local database. If there is a local patient record with the new NHS number, no further synchronisation between Medicus and the PDS will happen and a superseded PDS record task is then be created so that the practice can resolve the issue with Medicus. The existing local record is still usable for delivering care. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/superseded-pds-records¦https://medicus.scrollhelp.site/support/superseded-pds-records] |  |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Failure to update the patient record | HAZ-241 | 13 October 2022 | [6 empty] | Considerable | Low | 2 | There is a likelihood that there could be significant clinical risk. | Every day at 03:00 Medicus retrieves the updates PDS records of any patients with an active PDS link. Any fields that have changed on the PDS are then updated on the local patient record. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. |  |  |  |  | Considerable | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
HAZ-66 | Patient misidentification or inability to identify patient | Possible inappropriate care, delay to care, lack of care. | Inadequate performance of search algorithm | HAZ-146 | 6 August 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | The patient search uses an algorithm to return the correct patient records based on a number of factors. Full details can be found here: [https://medicus.scrollhelp.site/support/patient-finder¦https://medicus.scrollhelp.site/support/patient-finder] | We implement a large number of automated tests to prove that the code is functioning as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/patient-finder¦https://medicus.scrollhelp.site/support/patient-finder] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Inability to differentiate between patients with similar information | HAZ-283 | 5 December 2022 | [6 empty] | Considerable | High | 3 | The likelihood of an adverse consequence due to this cause presents an undesirable level of risk due to the patient being incorrectly identified from a list of similar names. | Multiple points of information are displayed on screen to the user when returning search results to enable them to correctly identify the patient. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/patient-finder¦https://medicus.scrollhelp.site/support/patient-finder] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The likelihood of an adverse consequence due to this cause can be mitigated through both design controls enabling clearer differentiation of patients within a list of patients with similar names. This along with training and organisational controls requiring users ensure they use additional information from the patient, further reduces risk. Whilst this reduces the likelihood of this occurrence, the severity is not reduced. These controls however reduce the risk to an acceptable level.
|  |  | Lack of context about which patient is selected | HAZ-147 | 6 August 2022 | [6 empty] | Considerable | High | 3 | There is a likelihood that there could be significant clinical risk. | Medicus consistently displays the patient banner clearly at the top of the screen so that the user always knows which patient record they interacting with. The patient banner confirms to NHS standards. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/identifying-which-patient-is-selected¦https://medicus.scrollhelp.site/support/identifying-which-patient-is-selected] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Inability to identify an inactive patient | HAZ-148 | 6 August 2022 | [6 empty] | Considerable | High | 3 | The likelihood of an adverse consequence due to this cause presents and undesirable level of risk due to the inability to select the correct patient or the patient being marked as inactive. | By default, inactive patients are excluded from the patient finder feature but users can optionally include them. This ability is prominently displayed on screen to the user. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/patient-finder¦https://medicus.scrollhelp.site/support/patient-finder] | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The likelihood of an adverse consequence due to this cause can be mitigated through both design controls and organisational controls. Simple design features displayed prominently greatly reduce the possibility of not being able to identify a patient even if they have been inappropriately deducted/marked as inactive. Whilst this reduces the likelihood of this occurrence to a very low level, the severity is not reduced. These controls however reduce the risk to an acceptable level.
|  |  | Duplicate patient records | HAZ-282 | 5 December 2022 | [6 empty] | Considerable | Low | 2 | The likelihood of an adverse consequence due to this cause presents and undesirable level of risk due to the incorrect patient being selected. | For organisations in England, Medicus checks for the existence of a local patient record using the same NHS number as the patient being registered. If a local patient record already exists then it becomes active again, otherwise a new local patient record is created. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/creating-a-new-safeguarding-case¦https://medicus.scrollhelp.site/support/creating-a-new-safeguarding-case] |  | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. | Considerable | Very Low | 2 | The likelihood of an adverse consequence due to this cause can be mitigated through both design controls and organisational controls requiring users ensure they use additional information from the patient to correctly identify them in Medicus. Whilst this reduces the likelihood of this occurrence to a very low level, the severity is not reduced. These controls however reduce the risk to an acceptable level.
|  |  | Patient changes key demographic information | HAZ-284 | 5 December 2022 | [6 empty] | Considerable | High | 3 | The likelihood of an adverse consequence due to this cause presents and undesirable level of risk due to the patient being incorrectly identified due to change in name or gender. |  |  |  |  | Individual users should obtain enough additonal information to correctly identify patients. Healthcare organisations should have a local policy for this. |  | Considerable | Low | 2 | The likelihood of an adverse consequence due to this cause can be mitigated primarily through organisational controls and business processes. These would require users ensure they use additional information from the patient to correctly identify the patient. Whilst this reduces the likelihood of this occurrence, the severity is not reduced. These controls however reduce the risk to an acceptable level.
|  |  | Patient incorrectly registered | HAZ-285 | 5 December 2022 | [6 empty] | Considerable | High | 3 | The likelihood of an adverse consequence due to this cause presents and undesirable level of risk due to the patient being incorrectly registered. |  |  |  |  | Individual users should obtain enough information to correctly identify patients. Healthcare organisations should have a local policy for this. Organisations also need to ensure there are clear processes to ensure a patient is correctly registered and minimising risk of registering the incorrect patient. |  | Considerable | Low | 2 | The likelihood of an adverse consequence due to this cause can be mitigated primarily through organisational controls and business process. Whilst this reduces the likelihood of this occurrence the severity is not reduced. This however reduces the risk to an acceptable level.

## Platform & Infrastructure
| Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk
ID | Hazard Description |  | Causes |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Hazard | Potential Clinical Impact | Possible Cause | Cause ID | Date Added | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
HAZ-60 | Medicus is unavailable | Inappropriate care due to inability to access patient records, delay to care. | Data centre power failure | HAZ-259 | 7 November 2022 |  |  |  |  | Healthcare organisations must have appropriate business continuity procedures in place. |  | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Server architecture splits across multiple “availability zones” with automatic failover of load balancer if one availability zone becomes unavailable. Database replication across multiple availability zones, with automatic failover of “master” database server if one availability zone becomes unavailable. | [https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html¦https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html] [https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html¦https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html] |  |  | Backup power supply at data centres | [https://aws.amazon.com/compliance/data-center/controls/¦https://aws.amazon.com/compliance/data-center/controls/] | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Data centre fire / environmental disaster | HAZ-260 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Server architecture splits across multiple “availability zones” with automatic failover of load balancer if one availability zone becomes unavailable. Database replication across multiple availability zones, with automatic failover of “master” database server if one availability zone becomes unavailable. | [https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html¦https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html] [https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html¦https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html] |  |  | Fire suppression systems and monitoring at data centres | [https://aws.amazon.com/compliance/data-center/controls/¦https://aws.amazon.com/compliance/data-center/controls/] | Major | Very Low | 2 | There is a likelihood that there could be significant clinical risk.
|  |  | Data centre network connection failure | HAZ-261 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Server architecture splits across multiple “availability zones” with automatic failover of load balancer if one availability zone becomes unavailable. Database replication across multiple availability zones, with automatic failover of “master” database server if one availability zone becomes unavailable. | [https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html¦https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html] [https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html¦https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html] |  |  | IT Service Continuity Management process, audited as part of ISO 27001 and NHS “Business Continuity” Overarching Standard |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Server mis-configuration | HAZ-262 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Infrastructure stored in version control as code (Terraform), to ensure transparent and audited infrastructure. |  |  |  | AWS Well Architected Framework review carried out and reviewed by NHS Digital. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Failure to renew domain name before expiry date | HAZ-263 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. |  |  |  |  | Automatic renewal reminders from OpenSRS (domain registrar) at 90, 60 and 30 days before expiry. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Failure to renew SSL certificate before expiry date | HAZ-264 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Automatic “managed renewal” of certificates where possible by AWS. | [https://docs.aws.amazon.com/acm/latest/userguide/managed-renewal.html¦https://docs.aws.amazon.com/acm/latest/userguide/managed-renewal.html] |  |  |  |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Failure to synchronise server clocks | HAZ-265 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | NTP Time Synchronisation enabled on all servers against AWS Time Sync Service. | [https://aws.amazon.com/about-aws/whats-new/2017/11/introducing-the-amazon-time-sync-service/¦https://aws.amazon.com/about-aws/whats-new/2017/11/introducing-the-amazon-time-sync-service/] |  |  |  |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Failure to deploy Medicus code | HAZ-266 | 7 November 2022 | [6 empty] | Major | Medium | 3 |  | Using Docker containers allows for a clean build and deploy. Automated deployment process using Octopus Deploy ([https://octopus.com/¦https://octopus.com/]) and AWS ECS ([https://aws.amazon.com/ecs/¦https://aws.amazon.com/ecs/]). |  |  |  | Build & deployment to a pre-production environment, with verification activities performed there, before deployment of the same built artefacts to the Production environment. Notifications to Slack by Octopus Deploy of any failed deployments. |  | Major | Low | 3
|  |  | Server resources not sufficient to service requests | HAZ-267 | 7 November 2022 | [6 empty] | Major | Medium | 3 |  | Automatic scaling of AWS ECS Services (launching more containers) based on load. | [https://docs.aws.amazon.com/AmazonECS/latest/developerguide/service-auto-scaling.html¦https://docs.aws.amazon.com/AmazonECS/latest/developerguide/service-auto-scaling.html] |  |  | Monitoring and alerting if services are over capacity. |  | Major | Low | 3
|  |  | Server hardware failure | HAZ-268 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Server architecture splits across multiple “availability zones” with automatic failover of load balancer if one availability zone becomes unavailable. Database replication across multiple availability zones, with automatic failover of “master” database server if one availability zone becomes unavailable. | [https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html¦https://docs.aws.amazon.com/whitepapers/latest/real-time-communication-on-aws/cross-region-dns-based-load-balancing-and-failover.html] [https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html¦https://docs.aws.amazon.com/AmazonRDS/latest/UserGuide/Concepts.MultiAZ.html] |  |  | IT Service Continuity Management process, audited as part of ISO 27001 and NHS “Business Continuity” Overarching Standard. |  | Major | Low | 3 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Cyber attack / denial of service attack | HAZ-269 | 7 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | All servers within private network (VPC) based on AWS Well Architected best practices. Use of AWS Web Application Firewall to filter traffic that appears to be a cyber attack / denial of service attack. | [https://aws.amazon.com/waf/¦https://aws.amazon.com/waf/] |  |  | Information Security Management System audited annually as part of ISO 27001 accreditation. Regular penetration tests from CREST-approved penetration testing company. |  | Major | Low | 3 | The residual likelihood is reduced based on additional mitigating controls.

## Safeguarding Case Management
| Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk
ID | Hazard Description |  | Causes |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Hazard | Potential Clinical Impact | Possible Cause | Cause ID | Date Added | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
HAZ-178 | Delay in processing safeguarding case | Delay to care, lack of care. | Foreseeable misuse of the Safeguarding Case Management module | HAZ-245 | 13 October 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. |  |  | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/safeguarding-case-management¦https://medicus.scrollhelp.site/support/safeguarding-case-management] | Healthcare organisations should have a local policy for record management and the use of Medicus should be in line with the organisational policy. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Case not entered into Medicus promptly and correctly | HAZ-246 | 13 October 2022 | [6 empty] | Major | High | 4 | There is a likelihood that there could be significant clinical risk. | The Medicus safeguarding case management module is specifically designed and constrained for the purpose of workflow management for safeguarding services. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/creating-a-new-safeguarding-case¦https://medicus.scrollhelp.site/support/creating-a-new-safeguarding-case] | Healthcare organisations should have their own local procedures for managing safeguarding cases. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Safeguarding case closed inappropriately | HAZ-247 | 13 October 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Before closing a safeguarding case, the user has to pass through a confirmation step which acts as an extra barrier to inappropriately closing the case. In the event that a user accidentally closes the case, it can be re-opened again. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/safeguarding-case-management¦https://medicus.scrollhelp.site/support/safeguarding-case-management] | Healthcare organisations should have their own local procedures for managing safeguarding cases. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | User misinterpretation of risk levels | HAZ-248 | 13 October 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | Risk levels are configurable by the local organisation so that they can be tailored to local policies and processes. When displaying the risk level of a safeguarding case, a text label always accompanies any use of colour for users with additional accessibility needs. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. |  |  | Healthcare organisations should have their own local policy for what each risk level means and the subsequent workflow. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Inability to view all open cases | HAZ-249 | 13 November 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | All safeguarding cases are visible from the user’s homepage. By default, the filter is set to only show open cases but this can be changed by the user. | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/safeguarding-case-management¦https://medicus.scrollhelp.site/support/safeguarding-case-management] | Healthcare organisations should have their own local procedures for managing safeguarding cases. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Case number identification errors | HAZ-250 | 13 October 2022 | [6 empty] | Major | Low | 3 | There is a likelihood that there could be significant clinical risk. | An internal case number is assigned to each new case (format SC-1). Whilst this is unique within the safeguarding service, it is not globally unique and therefore should not be used as such. Theoretically two patients from different safeguarding services could have the same internal ID number. In addition to the internal case number, users can also store a record of the external case/referral number (e.g. the one held generated by a Police system). | We implement a large number of automated tests to prove that the code is working as expected. These are described in the Medicus Test Report. |  |  | Healthcare organisations should have their own local procedures for managing safeguarding cases. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.
|  |  | Relevant information being missed in the case notes | HAZ-288 | 7 December 2022 | [6 empty] | Major | Medium | 3 | There is a likelihood that there could be significant clinical risk. | For information governance and safety reasons, there is currently no ability to delete a safeguarding case. When viewing a safeguarding case, the entire history of notes or attachments is displayed with no filter applied. |  | We provide a customer help centre in Confluence with appropriate training articles for using Medicus. | [https://medicus.scrollhelp.site/support/safeguarding-case-management¦https://medicus.scrollhelp.site/support/safeguarding-case-management] | Healthcare organisations should have their own local procedures for managing safeguarding cases. |  | Major | Very Low | 2 | The residual likelihood is reduced based on additional mitigating controls.